## Project Planner
Project Title
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.1 Assign roles in project | 1 | 1 | 1 | 1 | 100%
1.2 Set objective | 1 | 1 | 1 | 1 | 100%
1.3 Identify stakeholders | 1 | 1 | 1 | 1 | 100%
1.4 Define project scope | 1 | 1 | 1 | 1 | 100%
2.1 WBS | 2 | 2 | 2 | 2 | 100%
2.2 Activity Definitions | 2 | 1 | 2 | 1 | 100%
2.3 Gantt Chart | 4 | 1 | 4 | 1 | 100%
3.1 Define the system vision | 5 | 1 | 5 | 1 | 100%
3.2 Set software and user requrements | 6 | 1 | 6 | 1 | 100%
3.3 Use case diagrams and use cases | 7 | 2 | 7 | 2 | 100%
3.4 Software Design | 8 | 2 | 8 | 2 | 100%
3.5 User hierarchy chart | 10 | 1 | 10 | 1 | 100%
3.6 Design wireframes and mock-ups | 11 | 3 | 11 | 3 | 100%
4.1 Setup program code | 14 | 1 |  |  | 0%
4.2 Features implementation | 15 | 10 |  |  | 0%
4.2.1 Implement Food search | 25 | 5 |  |  | 0%
4.2.2 Nutrition breakdown | 25 | 5 |  |  | 0%
4.2.3 Nutrition range filter | 25 | 5 |  |  | 0%
4.2.4 Nutrition level filter | 30 | 5 |  |  | 0%
4.2.5 Weight calculation feature | 30 | 5 |  |  | 0%
4.3 User interface implementation | 30 | 5 |  |  | 0%
4.4 API implementation | 35 | 3 |  |  | 0%
5.1 Unit and Functional testing | 38 | 3 |  |  | 0%
5.2 Integration testing | 41 | 2 |  |  | 0%
5.3 User experience and use-case testing | 41 | 2 |  |  | 0%
5.4 Bug hunting | 41 | 2 |  |  | 0%
5.5 Acceptance testing | 43 | 2 |  |  | 0%
5.6 performance and optimisation | 43 | 2 |  |  | 0%
6.1 Finalising documentation | 45 | 1 |  |  | 0%
6.2 Logging hours/time sheets | 45 | 1 |  |  | 0%
6.3 Final handover to client | 45 | 1 |  |  | 0%
6.4 Performance review and gitlog | 46 | 1 |  |  | 0%